## Sheet1
DEV STAGE | Activity |  | Monday (all Planning) | Tuesday | Wednesday | Thursday | Friday | Saturday testing & debugging | Sunday | Monday
| Backend | Frontend
code | User Routes & models
code | Resume Routes & models
code | link routes together & create hierarchy
code | Create authenticated password with bcrypt
code | Create authenticated tokens
code | Disallow routes from unauthed users
code |  | Landing page
code |  | Profile link
code |  | Create resume button
code |  | Multistage resume form using Switch cases
code |  | "finalise resume" button
code |  | Send resume object to backend
code |  | add resumes to list in user profile page
code |  | register page
code |  | login page
code |  | authenticate routes on frontend using JWT
test | creating user
test | logging in
test | sending objects between hierarchy
test | test authed routes for unauthed users
test |  | logging in / registering
test |  | linking between pages working
test |  | layout on different displays
test |  | multistage form saves data after refresh
code | Upload to Heroku